Website Change Request Form Template

Fill in every [bracket], delete the guidance in italics, and send it as a PDF or a link. Written for web designers; works in Google Docs, Word, Notion or any proposal tool. Part 1 is the form. Part 2 is four reply emails. Part 3 is a filled-in example.

Part 1: Change Request Form

Project: [Client business name], [Website project name]

Change request no.: [CR-01]

Date: [Date]

Prepared by: [Your name], [Your studio]

Original proposal: [Proposal title and date]. Point back to it: the same terms and conditions apply to this change.

1. What the client asked for

One request per form. Three asks means three forms and three prices. Use the client's own words.

[Client contact name] asked on [date], by [email / call / message]: "[quote the request]".

2. Checked against the original scope

Open the accepted proposal and sort the request into one of these three piles.

[ ] Included. It is already covered by [scope line / revision round]. No change request needed. Do it, within the rounds left.

[ ] A fix. Something we built does not work as agreed. We will fix it at no charge.

[ ] New work. It is outside the original scope: [which line, or what the proposal says is not included].

3. What it adds

|  | Original | This change | New total |
| --- | --- | --- | --- |
| Fixed fee | [$ ____] | [+ $ ____] | [$ ____] |
| Pages | [__] | [+ __] | [__] |
| Business days | [__] | [+ __] | [__] |

Price it as a fixed fee when you can. If it is a small change, you may bill it on a time-and-materials basis at your standard hourly rate, as long as you say so here.

Launch date: moves from [date] to [date] if approved by [date].

4. The client's options

[ ] Approve the change as priced above.

[ ] Smaller version: [describe a cut-down option, with its own price and days].

[ ] Not now: hold it for [after launch / a later phase]. Nothing changes in the current project.

Offer the smaller version rather than a discount.

5. Payment

Fee for this change: [$ ____], [due now / invoiced separately when the work is done].

Each change request is invoiced on its own, so the original invoices stay unchanged.

Invoices are due [on receipt / within 15 days]. (Choose your terms and write the date down.)

6. When the feedback rounds apply

Date the client's side too.

A round is one list of feedback, from [one named person], within [5] business days of each draft. A second list is a new round.

If feedback, copy, photos or logins arrive late, the later dates move by the same number of days.

7. What counts as a big change

Optional. Decide a line in advance and write it down. If a change is bigger than [10]% of the schedule or budget, or [$1,000], whichever is greater, we will write a new proposal instead of a change request.

8. Approval

I approve change request [CR-01] as chosen above, for the price and days shown, and the same terms as the original proposal.

Option chosen: [ ____________ ]

Client name: [ ____________ ]  Date: [ ____________ ]

Signature or typed name: [ ____________ ]

[Your name], [Your studio]  Date: [ ____________ ]

Start the work after you have this written yes, not after the call.

Sending lots of these? Workspace369 turns a proposal into a link your client accepts with a typed name. Once accepted, the proposal locks, and on Specialist a later change goes through a change order the client approves, made in the app: https://workspace369.com/features/change-orders/?utm_source=template&utm_medium=download&utm_campaign=website-change-request-form-template&utm_content=accept

Part 2: Four reply emails

Send each in the same thread as the original request, so the history stays in one place. Change the numbers.

A. It is new work

Subject: Re: [their subject]

Hi [Name],

Thanks, I checked this against our scope. [The ordering page] is new work. It is [price] and adds [number] business days, so launch moves to [date]. The change request form is attached. Reply "approved" and I'll start.

[Your name]

B. It is already included

Subject: Re: [their subject]

Hi [Name],

Good news: this fits [revision round 2]. Send me one list of changes by [date] and I'll do them all.

[Your name]

C. It is a bug we will fix

Subject: Re: [their subject]

Hi [Name],

Thanks for catching that. It should work as we agreed, so I'm fixing it now at no charge. I'll tell you when it's live.

[Your name]

D. "That costs too much"

Subject: Re: [their subject]

Hi [Name],

Understood. Here is a smaller version: [describe it], for [price] and [number] days. Or we can hold the original request for after launch. Which would you like?

[Your name]

This template is general information, not legal advice. Have your terms checked by someone qualified where you work, especially payment, ownership and late-fee wording.

Template from the One Person Agency channel. Our #1 pick is Workspace369.

Part 3: Example, the same form filled in

A fictional studio and client, so you can see what "specific" looks like. Your numbers will differ.

Change Request CR-01 for Pine & Co. Bakery

Project: Pine & Co. website · Prepared by: Maya Reyes, Reyes Web Studio · Original proposal: Standard package, 6 pages, 2 revision rounds, $4,800 fixed fee

1. The ask. Jo Park asked by email on the 9th: "Can you also add an online ordering page, and tweak the homepage a bit more?"

2. Checked against scope. Ordering page: new work (not in the 6 pages). Homepage tweaks: included, they fit revision round 2.

3. What it adds.

|  | Original | This change | New total |
| --- | --- | --- | --- |
| Fixed fee | $4,800 | +$650 | $5,450 |
| Pages | 6 | +1 | 7 |
| Business days | 20 | +4 | 24 |

Launch moves from the 28th to the 3rd of next month if approved by the 14th.

4. Options. Approve the ordering page as priced · Smaller version: an order-by-email form on the Contact page, $150 and 1 day · Not now: hold the ordering page for after launch.

5. Payment. $650, invoiced separately when the page is done, due on receipt.

6. Rounds. The homepage tweaks are in round 2: one list from Jo within 5 business days. A second list would be a new round.

7. Big change. The line is the greater of 10% of the budget ($480) or $1,000, so $1,000. This change is $650, under the line, so it stays a change request.

8. Approval. Option: Approve. Accepted by Jo Park, typed name, on the 12th.

Fictional example. The studio, client and numbers are made up to illustrate the template.